## Project Overview
Smart Study Planner System
Smart Study Planner System is a web-based application designed to help students manage their academic responsibilities efficiently. The system allows users to: - Register and login securely - Add and manage courses - Create and track assignments and tasks - Generate weekly study plans based on deadlines and priorities - Receive reminders for upcoming tasks The goal of this project is to improve students’ time management and productivity by providing a structured planning system. Team Roles: - Fatma Nur Çetinkaya – Planning / Project Management - Berfin Nazlıcan Öztürk – Backend Developer - Damla Daştan – Frontend Developer - İbrahim Direk – Database Designer

## 12-Week Timeline
Week | Activities
1 | Project scope definition, requirement analysis, Jira setup
2 | User stories writing, backlog preparation
3 | System architecture design, technology stack selection
4 | Database design, ER diagram creation
5 | Use Case, Class and Sequence UML diagrams
6 | Backend project setup, authentication implementation
7 | Course and Task CRUD implementation
8 | Frontend UI design, wireframes creation
9 | Frontend development and backend integration
10 | Weekly planner logic implementation, notification system
11 | Testing, bug fixing, performance improvements
12 | Final documentation, demo preparation, GitHub submission

## Budget Planning
Name | Role | Estimated Hours | Hourly Rate (TL) | Labor Cost (TL)
Fatma Nur Çetinkaya | Planning / PM | 40 | 150 | 6000
Berfin Nazlıcan Öztürk | Backend Developer | 60 | 150 | 9000
Damla Daştan | Frontend Developer | 60 | 150 | 9000
İbrahim Direk | Database Designer | 40 | 150 | 6000
|  |  | Total Labor | 30000
Hosting (Estimated) |  |  |  | 500
Tools / Misc (Estimated) |  |  |  | 300
TOTAL PROJECT COST |  |  |  | 30800